## Product_Backlog
Total Features | Left | Available | Completed | Sprint Ends
Total at Start | 32 | 32
Sprint 1 | 32 | 32 | 1 | 2017-03-28
Sprint 2 | 31 | 32 | 1 | 2017-04-04
Sprint 3 | 31 | 32 | 3 | 2017-04-11
Sprint 4 | 29 | 32 | 7 | 2017-04-18
Sprint 5 | 25 | 32 | 10 | 2017-04-25
Sprint 6 | 22 | 32 | 10 | 2017-05-02
Sprint # (by team size)
Feature ID | Prio | Status | Actual Sprint # | 1 | 2 | 3 | 4 | Pts | Cml | As a... | I want to... | So that... | Type | Notes
Parts_Creation | 1 | CO | 1 | 1 | 1 | 1 | 1 | 21 | 21 | PM | create robot parts | I can define robot models | CLI | No menu required here – run program, create a part
Model_Creation | 2 | CO | 5 | 2 | 1 | 1 | 1 | 13 | 34 | PM | define new robot models | RRS can sell them to our Beloved Customers | CLI | Menu needed – create parts, then create a robot model
Model_Creation | 3 | CO | 5 | 2 | 1 | 1 | 1 | 5 | 39 | BC | browse a catalog of robot models | I can buy one or more robots | CLI | Need to list robots models, then list parts in selected model
Customer_Creation | 4 | CO | 3 | 3 | 2 | 1 | 1 | 3 | 42 | PB | create a new Beloved Customer | I can keep track of who's buying our products | CLI | The usual name, customer number, phone number, and email address
Associate_Creation | 5 | CO | 3 | 3 | 2 | 1 | 1 | 3 | 45 | PB | create a new Sales Associate | I can keep track of my employees' performance | CLI | Name and employee number at a minimum
Order_Model | 6 | IW | 3 | 3 | 2 | 2 | 1 | 8 | 53 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | CLI | Select robot model and quantity, show details with total price
File I/O | 7 | NS | 3 | 3 | 2 | 2 | 2 | 13 | 66 | PB | ensure persistence of the RRS data | we don't lose orders or historical data | CLI | (CLI) Write the data to the default filename and reload it next time the program runs
Gui_Create | 8 | CO | 4 | 4 | 3 | 2 | 2 | 3 | 69 | All | open a GUI main window | I can interact with RRS Manager with my mouse | GUI | No menu required here – run program, create a part
Gui_Create | 9 | CO | 4 | 4 | 3 | 2 | 2 | 34 | 103 | PM | create robot parts via GUI dialogs | I can define robot models | GUI | An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
Gui_Model_Create | 10 | CO | 5 | 5 | 4 | 3 | 3 | 21 | 124 | PM | define new robot models via GUI dialogs | RRS can sell them to our Beloved Customers | GUI | Similar to robot parts (perhaps Create > Robot Model)
| 11 | NS | 6 | 6 | 4 | 3 | 3 | 8 | 132 | BC | browse a catalog of robots via a GUI report | I can buy one or more robots | GUI | A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
| 12 | NS |  |  | 5 | 4 | 3 | 21 | 153 | SA | create a robot order for a Customer via GUI | I can sell robots and thus do my job well | GUI | As with CLI (and you’ll need the CLI to add BC and SA people)
| 13 | NS |  |  | 5 | 4 | 4 | 13 | 166 | PB | manage a robot order for a Customer via GUI | I can ensure the robot is built and ships | GUI | This will involve a state machine implementation
Cust_GUI_Create | 14 | CO | 4 |  | 5 | 4 | 4 | 8 | 174 | PB | create a new Beloved Customer via GUI | I can keep track of who's buying our products | GUI | The usual name, address, phone number, and email address (perhaps Create > Customer)
Assoc_GUI_Create | 15 | CO | 4 |  | 5 | 4 | 4 | 5 | 179 | PB | create a new Sales Associate via GUI | I can keep track of my employees' performance | GUI | Name and employee number at a minimum (perhaps Create > Sales Associate)
| 16 | NS |  |  | 6 | 5 | 4 | 13 | 192 | BC | see pictures of the robots in the GUI catalog | I can see what I'm buying | GUI | Add picture when defining robot model, and show it in the robot model report
| 17 | NS |  |  | 6 | 5 | 4 | 5 | 197 | PB | allow the users to save data explicitly via GUI | we can save data without exiting the program | GUI | Write the data to the default filename on command (perhaps File > Save to the default filename)
| 18 | NS |  |  | 6 | 5 | 4 | 8 | 205 | PB | allow the users to load data explicitly via GUI | we can manage multiple stores in different files | GUI | Read the data from a user-selected file on command (perhaps File > Open)
| 19 | NS |  |  | 6 | 5 | 4 | 8 | 213 | PB | allow the users to save data to a specified name via GUI | we can manage multiple stores in different files | GUI | Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
| 20 | NS |  |  |  | 5 | 5 | 13 | 226 | PB / SA | view a report of orders per SA in the GUI | I can estimate the value of employees / I can justify a raise | GUI | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 21 | NS |  |  |  | 6 | 5 | 21 | 247 | All | enable basic login by role and customize the GUI | we don't have options that don't apply to our roles | GUI | User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
| 22 | NS |  |  |  | 6 | 5 | 13 | 260 | All | enable copy and paste from text fields | we can save typing | GUI | Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
| 23 | NS |  |  |  | 6 | 6 | 13 | 273 | BC | view my bill (invoice) in the GUI | I can pay for my robots | GUI | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
| 24 | NS |  |  |  |  | 6 | 8 | 281 | BC | view my orders in the GUI | see what I have coming to me | GUI | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
| 25 | NS |  |  |  |  | 6 | 8 | 289 | SA | view a sales report in the GUI | I can justify a raise | GUI | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 26 | NS |  |  |  |  | 6 | 8 | 297 | PB | view a report of all orders in the GUI | I can manage the company | GUI | A basic text report is fine (perhaps Report > All Orders)
| 27 | NS |  |  |  |  | 6 | 13 | 310 | All | Add multi-level undo | Worry less about making mistakes | GUI | This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
| 28 | NS | [5 empty] | 21 | 331 | BC | see a pie chart of a model's component costs | I can decide if I want a different model | GUI | Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
| 29 | NS | [5 empty] | 13 | 344 | SA | create a bulk (2+) order for Customer via GUI | avoid proliferation of orders and paperwork | GUI | Allow more than one robot model (with respective quantity) on a single order
| 30 | NS | [5 empty] | 8 | 352 | PM | hide robot parts via GUI | obsolete parts aren't accidentally used | GUI | Mark robot parts as “obsolete” and don't allow adding them to new robot models
| 31 | NS | [5 empty] | 8 | 360 | PM | hide robot models via GUI | obsolete robots aren't ordered | GUI | Mark robot models as “obsolete” and don't allow adding them to new orders
| 32 | NS | [5 empty] | 21 | 381 | SA | save a draft order and return to it later via GUI | I can multi-task between indecisive customers | GUI | Save an order that hasn't been complete, and allow SA to resume work on it later
Formulas:
Sprint Ends = [Sprint Ends, row above]+7
Note on C34: NS = Not Started IW = In Work IT = In Test CP = Complete

## Sprint_NN_Backlog
Sprint # | 1 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2017-03-21
End on | 2017-03-28
Demo on
Total Tasks | 13
Day 1 Left | 10
Day 2 Left | 10
Day 3 Left | 9
Day 4 Left | 5
Day 5 Left | 5
Day 6 Left | 2
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Parts_Creation | Architecture | UML | JF | Creating/Add to Case/UML | CO
| Parts_Creation | Architecture | UML | JF | Fill in missing categories | CO
| Parts_Creation | Robot_Part | Code | JF | Complete the class | CO
| Parts_Creation | Robot_Part | Code | JF | Inherit the other Class parts and call for user input | CO
| Parts_Creation | Robot_Part | Test | JF | Test for user input towards a part | CO
| Parts_Creation | Head | Code | JF | Create selection input for part | CO
| Parts_Creation | Arm | Code | JF | Create selection input for part | CO
| Parts_Creation | Locomotor | Code | JF | Create selection input for part | CO
| Parts_Creation | Battery | Code | JF | Create selection input for part | CO
| Parts_Creation | Torso | Code | JF | Create selection input for part | CO
| Parts_Creation | Architecture | UML | JF | Unable to save/Crashed before screenshot | IW
| Parts_Creation | Main | Test | JF | Test code for use input | CO

## Sprint_NN_Backlog_2
Sprint # | 2
Start on | 2017-03-28
End on | 2017-04-04
Demo on
Total Tasks | 22
Day 1 Left | 22
Day 2 Left | 12
Day 3 Left | 12
Day 4 Left | 12
Day 5 Left | 10
Day 6 Left | 10
Day 7 Left | 8
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Model_Creation | Architecture | UML | JF | Recreate UML from previous crash | CO
| Model_Creation | Architecture | UML | JF | Fill in missing categories | CO
| Model_Creation | Robot_Part | Code | JF | Change class to use Polymorphism | CO
| Model_Creation | Robot_Part | Code | JF | Edit code to supply base method | CO
| Model_Creation | Robot_Part | Test | JF | Test for user input towards a part | CO
| Model_Creation | Head | Code | JF | Change method to_string to have its own saved variables | CO
| Model_Creation | Arm | Code | JF | Change method to_string to have its own saved variables | CO
| Model_Creation | Locomotor | Code | JF | Change method to_string to have its own saved variables | CO
| Model_Creation | Battery | Code | JF | Change method to_string to have its own saved variables | CO
| Model_Creation | Torso | Code | JF | Change method to_string to have its own saved variables | CO
| Model_Creation | Architecture | UML | JF | Update UML to match new functions | CO
| Model_Creation | Main | Test | JF | Test code for use input for each part to be saved into a vector | CO
| Model_Creation | Controller | Code | JF | Create classes to use Robot_parts to store different parts based on menu | CO
| Model_Creation | View | Code | JF | Create a menu to satisfy input conditions | CO
| Model_Creation | Robot_Model | Code | JF | Create class | CO
| Model_Creation | Robot_Model | Code | JF | Attach Robot_parts to Robot model | IW
| Model_Creation | Robot_Model | Code | JF | From Robot_parts vector list all the parts and select to create a model | IW
| Model_Creation | Shop | Code | JF | Create code to create a robot model | NS
| Model_Creation | Robot_Model | Code | JF | Create a vector that can store all the created models once completed | NS
| Model_Creation | Robot_Model | Code | JF | Make a catalog of all the existing models as well as parts | IW
| Model_Creation | Robot_Model | Test | JF | Test code to check if possible to create a model | IW
| Model_Creation | Robot_Model | Test | JF | Test code to view catalog of models | IW
| Model_Creation | Robot_Part | Test | JF | Make sure separate parts are being stored for robot_models for values | IW

## Sprint_NN_Backlog_3
Sprint # | 3
Start on | 2017-04-04
End on | 2017-04-11
Demo on
Total Tasks | 28
Day 1 Left | 28
Day 2 Left | 25
Day 3 Left | 25
Day 4 Left | 20
Day 5 Left | 20
Day 6 Left | 16
Day 7 Left | 15
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Customer_Creation | Customer | Code | JF | Create a Customer class | CO
| Customer_Creation | Customer | Code | JF | Change the cmd to function with a new prompt | CO
| Customer_Creation | Customer | Code | JF | Create a vector that can store the Customer data | CO
| Customer_Creation | Customer | Code | JF | List all the customer from the stored data | CO
| Customer_Creation | Customer | Test | JF | Test that we can create a customer | CO
| Customer_Creation | Customer | Test | JF | Test that we can see all the customers in the system | CO
| Customer_Creation | Architecture | UML | JF | Update UML to match new functions | CO
| Associate_Creation | Associate | Code | JF | Create an Associate Class | CO
| Associate_Creation | Associate | Code | JF | Add a new prompt to the CMD function | CO
| Associate_Creation | Associate | Code | JF | Create a vector that can store the Associate data | CO
| Associate_Creation | Associate | Code | JF | List all the associates from the stored data | CO
| Associate_Creation | Associate | Test | JF | Test that we can create an associate | CO
| Associate_Creation | Associate | Test | JF | Test that we can see all the associates in the system | CO
| Associate_Creation | Architecture | UML | JF | Update UML to match new functions | CO
| Associate_Creation | Associate | Code | JF | Create class | CO
| Parts_Creation | Robot_Parts | Code | JF | Fix from Sprint 2 to save into a vector again | CO
| Parts_Creation | Robot_Parts | Code | JF | Create the Robot_model from Sprint 2 | IW
| Order_Model | Order | Code | JF | Create the Order Class | CO
| Order_Model | Order | Code | JF | Organize functions to place an order for an existing model | NS
| Order_Model | Order | Code | JF | Keep track of Models that were bought with a separate vector | NS
| Order_Model | Order | Code | JF | Be able to show descriptions of the robot model with prices for the order | NS
| Order_Model | Order | Test | JF | Test code to place an order for a Robot_model | NS
| Order_Model | Order | Code | JF | Connect customers so that they may purchase such models | NS
| Order_Model | Order | Test | JF | Test that a customer can be shown buying a model | NS
| File I/O | Save | Code | JF | Create functions to save the data | NS
| File I/O | Save | Test | JF | Test whether a file can be saved | NS
| Order_Model | Architecture | UML | JF | Update UML to match new functions | NS
| File I/O | Architecture | UML | JF | Update UML to match new functions | NS

## Sprint_NN_Backlog_4
Sprint # | 4 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2017-04-11
End on | 2017-04-18
Demo on
Total Tasks | 27
Day 1 Left | 27
Day 2 Left | 27
Day 3 Left | 27
Day 4 Left | 27
Day 5 Left | 12
Day 6 Left | 7
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Gui_create | Architecture | UML | JF | Create/Add a Box Class(Global) To UML | CO
| Gui_create | Controller | Code | JF | Edit existing classes I.E. Controller/View | CO
| Gui_create | Controller | Code | JF | Edit Add Head in Controller to utilize GUI | CO
| Gui_create | Controller | Code | JF | Edit Add Locomotor in Controller to utilize GUI | CO
| Gui_create | Controller | Code | JF | Edit Add Battery in Controller to utilize GUI | CO
| Gui_create | Controller | Code | JF | Edit Add Arm in Controller to utilize GUI | CO
| Gui_create | Controller | Code | JF | Edit Add Torso in Controller to utilize GUI | CO
| Gui_create | Box | Code | JF | Create Box Class | CO
| Gui_create | Box | Code | JF | Use the Box to create a Dialog Menu | CO
| Gui_create | Box | Code | JF | Attach Box to Storage and View to add them to GUI | CO
| Gui_create | GUI | Test | JF | Test code to make sure a Dialog Opens | CO
| Gui_create | Sub_menu | Code | JF | Create a Submenu | CO
| Gui_create | Callbacks | Code | JF | Create a Callback Section | CO
| Gui_create | Callbacks | Code | JF | Attach Callbacks to execute_cmd calls in Controller | CO
| Gui_create | Callbacks | Code | JF | Attach Callbacks to the submenu to function as actions | CO
| Gui_create | Main | Code | JF | In Main create actions necessary to open/view dialog | CO
| Gui_create | GUI | Test | JF | Test Options for adding a part for each individual part | CO
| Cust_GUI_Create | Controller | Code | JF | Edit Adding a Customer in Controller to utilize Gui | CO
| Assoc_GUI_Create | Controller | Code | JF | Edit Adding an Associate in Controller to utilize GUI | CO
| Cust_GUI_Create | Controller | Code | JF | Edit List parts/Customer/Associates to utilize GUI in controller | CO
| Cust_GUI_Create | GUI | Test | JF | Test Code to make sure Customer works with GUI | CO
| Assoc_GUI_Create | GUI | Test | JF | Test code to make sure Associate works with GUI | CO
| Gui_create | General | Code | JF | Work out the Bugs(may be many) | CO
| Gui_create | GUI | Test | JF | Test if can list parts | CO
| Cust_GUI_Create | GUI | Test | JF | Test if can list customers | CO
| Assoc_GUI_Create | GUI | Test | JF | Test if can list Associates | CO
| Gui_create | Architecture | UML | JF | Update any additional info to UML class diagram if needed | CO

## Sprint_NN_Backlog_5
Sprint # | 5 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2017-04-18
End on | 2017-04-25
Demo on
Total Tasks | 12
Day 1 Left | 12
Day 2 Left | 12
Day 3 Left | 10
Day 4 Left | 8
Day 5 Left | 8
Day 6 Left | 5
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Gui_Model_Create | Architecture | UML | JF | Edit UML for any added methods | CO
| Gui_Model_Create | Controller | Code | JF | Edit existing classes I.E. Controller/View | CO
| Gui_Model_Create | Controller | Code | JF | Edit Current Add Model to finally work | CO
| Gui_Model_Create | Controller | Code | JF | Edit Create Model in Controller for GUI | CO
| Gui_Model_Create | Storage | Code | JF | Create a Vector to store model | CO
| Gui_Model_Create | Controller | Code | JF | Edit Storage/View to gather Model Data | CO
| Gui_Model_Create | Controller | Test | JF | Test code to make sure a Dialog Opens | CO
| Gui_Model_Create | Sub_menu | Code | JF | Attach a Callback Section Model | CO
| Gui_Model_Create | Sub_menu | Code | JF | Attach a Submenu for Model | CO
| Gui_Model_Create | GUI | Test | JF | Test code to add a model on dialog | CO
| Gui_Model_Create | GUI | Test | JF | Test to list Models | CO | Seg Faults when listing models, View has get list, storage has the rest of info on vector. List Parts lists the model perfectly fine with some added bugs.
| Gui_Model_Create | Architecture | UML | JF | Update any additional info to UML class diagram if needed | CO

## Sprint_NN_Backlog_6
Sprint # | 6 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2017-04-25
End on | 2017-05-02
Demo on
Total Tasks | 7
Day 1 Left | 7
Day 2 Left | 7
Day 3 Left | 5
Day 4 Left | 5
Day 5 Left | 2
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| Model_Catalog | Architecture | UML | JF | Edit UML for any added methods | CO
| Model_Catalog | Controller | Code | JF | Edit List Models from previous sprint progress to work correctly | CO
| Model_Catalog | Controller | Test | JF | Test the the Models can show the catalog alone with its parts | CO
| Model_Catalog | Controller | Code | JF | Work out any remaining bugs in the Catalog for Models | CO
| Model_Catalog | Controller | Test | JF | Test the callback from the dialog for List Models | CO
| Model_Catalog | Controller | Test | JF | Test for multiple parts for Models to ensure no Seg Faults | CO
| Model_Catalog | Architecture | UML | JF | Update any additional info to UML class diagram if needed | CO