## Product_Backlog
Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	1	Mar 28
Sprint 2	31	32	1	Apr 04
Sprint 3	31	32	3	Apr 11
Sprint 4	29	32	7	Apr 18
Sprint 5	25	32	10	Apr 25
Sprint 6	22	32	10	May 02

				Sprint # (by team size)
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
Parts_Creation	1	CO	1	1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
Model_Creation	2	CO	5	2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
Model_Creation	3	CO	5	2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
Customer_Creation	4	CO	3	3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
Associate_Creation	5	CO	3	3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
Order_Model	6	IW	3	3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
File I/O	7	NS	3	3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
Gui_Create	8	CO	4	4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
Gui_Create	9	CO	4	4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
Gui_Model_Create	10	CO	5	5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
	11	NS	6	6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
Cust_GUI_Create	14	CO	4		5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
Assoc_GUI_Create	15	CO	4		5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS						21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS						13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS						8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS						8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS						21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_NN_Backlog
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	3/21/17 12:00 AM
End on	3/28/17 12:00 AM
Demo on

Total Tasks	13
Day 1 Left	10
Day 2 Left	10
Day 3 Left	9
Day 4 Left	5
Day 5 Left	5
Day 6 Left	2
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Parts_Creation	Architecture	UML	JF	Creating/Add to Case/UML	CO
	Parts_Creation	Architecture	UML	JF	Fill in missing categories	CO
	Parts_Creation	Robot_Part	Code	JF	Complete the class	CO
	Parts_Creation	Robot_Part	Code	JF	Inherit the other Class parts and call for user input	CO
	Parts_Creation	Robot_Part	Test	JF	Test for user input towards a part	CO
	Parts_Creation	Head	Code	JF	Create selection input for part	CO
	Parts_Creation	Arm	Code	JF	Create selection input for part	CO
	Parts_Creation	Locomotor	Code	JF	Create selection input for part	CO
	Parts_Creation	Battery	Code	JF	Create selection input for part	CO
	Parts_Creation	Torso	Code	JF	Create selection input for part	CO
	Parts_Creation	Architecture	UML	JF	Unable to save/Crashed before screenshot	IW
	Parts_Creation	Main	Test	JF	Test code for use input	CO
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_2
Sprint #	2
Start on	3/28/17 12:00 AM
End on	4/4/17 12:00 AM
Demo on

Total Tasks	22
Day 1 Left	22
Day 2 Left	12
Day 3 Left	12
Day 4 Left	12
Day 5 Left	10
Day 6 Left	10
Day 7 Left	8

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Model_Creation	Architecture	UML	JF	Recreate UML from previous crash	CO
	Model_Creation	Architecture	UML	JF	Fill in missing categories	CO
	Model_Creation	Robot_Part	Code	JF	Change class to use Polymorphism	CO
	Model_Creation	Robot_Part	Code	JF	Edit code to supply base method	CO
	Model_Creation	Robot_Part	Test	JF	Test for user input towards a part	CO
	Model_Creation	Head	Code	JF	Change method to_string to have its own saved variables	CO
	Model_Creation	Arm	Code	JF	Change method to_string to have its own saved variables	CO
	Model_Creation	Locomotor	Code	JF	Change method to_string to have its own saved variables	CO
	Model_Creation	Battery	Code	JF	Change method to_string to have its own saved variables	CO
	Model_Creation	Torso	Code	JF	Change method to_string to have its own saved variables	CO
	Model_Creation	Architecture	UML	JF	Update UML to match new functions	CO
	Model_Creation	Main	Test	JF	Test code for use input for each part to be saved into a vector	CO
	Model_Creation	Controller	Code	JF	Create classes to use Robot_parts to store different parts based on menu	CO
	Model_Creation	View	Code	JF	Create a menu to satisfy input conditions	CO
	Model_Creation	Robot_Model	Code	JF	Create class	CO
	Model_Creation	Robot_Model	Code	JF	Attach Robot_parts to Robot model	IW
	Model_Creation	Robot_Model	Code	JF	From Robot_parts vector list all the parts and select to create a model	IW
	Model_Creation	Shop	Code	JF	Create code to create a robot model	NS
	Model_Creation	Robot_Model	Code	JF	Create a vector that can store all the created models once completed	NS
	Model_Creation	Robot_Model	Code	JF	Make a catalog of all the existing models as well as parts	IW
	Model_Creation	Robot_Model	Test	JF	Test code to check if possible to create a model	IW
	Model_Creation	Robot_Model	Test	JF	Test code to view catalog of models	IW
	Model_Creation	Robot_Part	Test	JF	Make sure separate parts are being stored for robot_models for values	IW
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_3
Sprint #	3
Start on	4/4/17 12:00 AM
End on	4/11/17 12:00 AM
Demo on

Total Tasks	28
Day 1 Left	28
Day 2 Left	25
Day 3 Left	25
Day 4 Left	20
Day 5 Left	20
Day 6 Left	16
Day 7 Left	15

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Customer_Creation	Customer	Code	JF	Create a Customer class	CO
	Customer_Creation	Customer	Code	JF	Change the cmd to function with a new prompt	CO
	Customer_Creation	Customer	Code	JF	Create a vector that can store the Customer data	CO
	Customer_Creation	Customer	Code	JF	List all the customer from the stored data	CO
	Customer_Creation	Customer	Test	JF	Test that we can create a customer	CO
	Customer_Creation	Customer	Test	JF	Test that we can see all the customers in the system	CO
	Customer_Creation	Architecture	UML	JF	Update UML to match new functions	CO
	Associate_Creation	Associate	Code	JF	Create an Associate Class	CO
	Associate_Creation	Associate	Code	JF	Add a new prompt to the CMD function	CO
	Associate_Creation	Associate	Code	JF	Create a vector that can store the Associate data	CO
	Associate_Creation	Associate	Code	JF	List all the associates from the stored data	CO
	Associate_Creation	Associate	Test	JF	Test that we can create an associate	CO
	Associate_Creation	Associate	Test	JF	Test that we can see all the associates in the system	CO
	Associate_Creation	Architecture	UML	JF	Update UML to match new functions	CO
	Associate_Creation	Associate	Code	JF	Create class	CO
	Parts_Creation	Robot_Parts	Code	JF	Fix from Sprint 2 to save into a vector again	CO
	Parts_Creation	Robot_Parts	Code	JF	Create the Robot_model from Sprint 2	IW
	Order_Model	Order	Code	JF	Create the Order Class	CO
	Order_Model	Order	Code	JF	Organize functions to place an order for an existing model	NS
	Order_Model	Order	Code	JF	Keep track of Models that were bought with a separate vector	NS
	Order_Model	Order	Code	JF	Be able to show descriptions of the robot model with prices for the order	NS
	Order_Model	Order	Test	JF	Test code to place an order for a Robot_model	NS
	Order_Model	Order	Code	JF	Connect customers so that they may purchase such models	NS
	Order_Model	Order	Test	JF	Test that a customer can be shown buying a model	NS
	File I/O	Save	Code	JF	Create functions to save the data	NS
	File I/O	Save	Test	JF	Test whether a file can be saved	NS
	Order_Model	Architecture	UML	JF	Update UML to match new functions	NS
	File I/O	Architecture	UML	JF	Update UML to match new functions	NS
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_4
Sprint #	4				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4/11/17 12:00 AM
End on	4/18/17 12:00 AM
Demo on

Total Tasks	27
Day 1 Left	27
Day 2 Left	27
Day 3 Left	27
Day 4 Left	27
Day 5 Left	12
Day 6 Left	7
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Gui_create	Architecture	UML	JF	Create/Add a Box Class(Global) To UML	CO
	Gui_create	Controller	Code	JF	Edit existing classes I.E. Controller/View	CO
	Gui_create	Controller	Code	JF	Edit Add Head in Controller to utilize GUI	CO
	Gui_create	Controller	Code	JF	Edit Add Locomotor in Controller to utilize GUI	CO
	Gui_create	Controller	Code	JF	Edit Add Battery in Controller to utilize GUI	CO
	Gui_create	Controller	Code	JF	Edit Add Arm in Controller to utilize GUI	CO
	Gui_create	Controller	Code	JF	Edit Add Torso in Controller to utilize GUI	CO
	Gui_create	Box	Code	JF	Create Box Class	CO
	Gui_create	Box	Code	JF	Use the Box to create a Dialog Menu	CO
	Gui_create	Box	Code	JF	Attach Box to Storage and View to add them to GUI	CO
	Gui_create	GUI	Test	JF	Test code to make sure a Dialog Opens	CO
	Gui_create	Sub_menu	Code	JF	Create a Submenu	CO
	Gui_create	Callbacks	Code	JF	Create a Callback Section	CO
	Gui_create	Callbacks	Code	JF	Attach Callbacks to execute_cmd calls in Controller	CO
	Gui_create	Callbacks	Code	JF	Attach Callbacks to the submenu to function as actions	CO
	Gui_create	Main	Code	JF	In Main create actions necessary to open/view dialog	CO
	Gui_create	GUI	Test	JF	Test Options for adding a part for each individual part	CO
	Cust_GUI_Create	Controller	Code	JF	Edit Adding a Customer in Controller to utilize Gui	CO
	Assoc_GUI_Create	Controller	Code	JF	Edit Adding an Associate in Controller to utilize GUI	CO
	Cust_GUI_Create	Controller	Code	JF	Edit List parts/Customer/Associates to utilize GUI in controller	CO
	Cust_GUI_Create	GUI	Test	JF	Test Code to make sure Customer works with GUI	CO
	Assoc_GUI_Create	GUI	Test	JF	Test code to make sure Associate works with GUI	CO
	Gui_create	General	Code	JF	Work out the Bugs(may be many)	CO
	Gui_create	GUI	Test	JF	Test if can list parts	CO
	Cust_GUI_Create	GUI	Test	JF	Test if can list customers	CO
	Assoc_GUI_Create	GUI	Test	JF	Test if can list Associates	CO
	Gui_create	Architecture	UML	JF	Update any additional info to UML class diagram if needed	CO
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_5
Sprint #	5				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4/18/17 12:00 AM
End on	4/25/17 12:00 AM
Demo on

Total Tasks	12
Day 1 Left	12
Day 2 Left	12
Day 3 Left	10
Day 4 Left	8
Day 5 Left	8
Day 6 Left	5
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Gui_Model_Create	Architecture	UML	JF	Edit UML for any added methods	CO
	Gui_Model_Create	Controller	Code	JF	Edit existing classes I.E. Controller/View	CO
	Gui_Model_Create	Controller	Code	JF	Edit Current Add Model to finally work	CO
	Gui_Model_Create	Controller	Code	JF	Edit Create Model in Controller for GUI	CO
	Gui_Model_Create	Storage	Code	JF	Create a Vector to store model	CO
	Gui_Model_Create	Controller	Code	JF	Edit Storage/View to gather Model Data	CO
	Gui_Model_Create	Controller	Test	JF	Test code to make sure a Dialog Opens	CO
	Gui_Model_Create	Sub_menu	Code	JF	Attach a Callback Section Model	CO
	Gui_Model_Create	Sub_menu	Code	JF	Attach a Submenu for Model	CO
	Gui_Model_Create	GUI	Test	JF	Test code to add a model on dialog	CO
	Gui_Model_Create	GUI	Test	JF	Test to list Models	CO	Seg Faults when listing models, View has get list, storage has the rest of info on vector. List Parts lists the model perfectly fine with some added bugs.
	Gui_Model_Create	Architecture	UML	JF	Update any additional info to UML class diagram if needed	CO
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_6
Sprint #	6				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4/25/17 12:00 AM
End on	5/2/17 12:00 AM
Demo on

Total Tasks	7
Day 1 Left	7
Day 2 Left	7
Day 3 Left	5
Day 4 Left	5
Day 5 Left	2
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
	Model_Catalog	Architecture	UML	JF	Edit UML for any added methods	CO
	Model_Catalog	Controller	Code	JF	Edit List Models from previous sprint progress to work correctly	CO
	Model_Catalog	Controller	Test	JF	Test the the Models can show the catalog alone with its parts	CO
	Model_Catalog	Controller	Code	JF	Work out any remaining bugs in the Catalog for Models	CO
	Model_Catalog	Controller	Test	JF	Test the callback from the dialog for List Models	CO
	Model_Catalog	Controller	Test	JF	Test for multiple parts for Models to ensure no Seg Faults	CO
	Model_Catalog	Architecture	UML	JF	Update any additional info to UML class diagram if needed	CO
Sprint Burn Chart
Days
Tasks